## Sheet1
Tasks | October 7th | 8th | 9th | 10th | 11th | 12th | 13th | 14th | 15th | 16th | 17th | 18th | 19th | 20th | 21st | 22nd | 23rd | 24th | 25th | 26th | 27th | 28th | 29th | 30th | 31st | 1st | 2nd | 3rd | 4th | 5th | 6th | 7th | 8th | 9th | 10th | 11th | 12th | 13th | 14th | 15th | 16th | 17th | 18th | 19th | 20th | 21st | 22nd | 23rd | 24th | 25th
Project Selection |  | 14th: Fall Break; 22nd: Code Freeze First Evaluation; 21st: Thanksgiving Break
Language and Platform Selection | bar: 17th to 18th
Planning of Implementation | bar: 18th to 20th
Initial code writing | bar: 19th to 21st
Character Development | bar: 19th to 21st; 25th to 27th
Portal Development | bar: 19th to 21st; 25th to 27th
Scene Development | bar: 20th to 21st; 25th to 27th
Basic Functionality Testing | bar: 20th to 21st; 25th to 6th
Level Design | bar: 25th to 6th
Menus and Replay Functionality | bar: 1st to 8th
Enemies Development | bar: 1st to 14th
Other Added Features | bar: 4th to 17th
Final Testing | bar: 10th to 20th